## Versions released and goals
Last Update: 10/5/2023 | v0 (archived) | v1 (archived) | v1.1 (archived) | v1.2 (archived) | v1.3 (archived) | v1.4 - CURRENT | Short term goals 1 | Short term goals 2 | Long term goals
Official Merge Date | 2022-11-21 | 2023-07-31
Summary | Prototype | Useable pipeline for local matches (combined with legacy preprocessing) | Added zip/county information for non-local matches, flexible acceptance criteria (to run full DCFS undup and secondary match for Family Networks project) | Complete pipeline for generating match crosswalk (using v1.1 logic) | Fixed performance issue with large datasets |  | Make the current version smooth | Go deeper into some of the "for later" problems | Dreams
Update - match logic | Designed and implemented prototype match logic, including blocking strategies, similarity metrics, acceptance criteria | Improved match logic accuracy | Added zip/county into match logic |  |  |  | Replace soundex with double-metaphone | Refine weight calculation based on review of match analysis and samples from prototype tests | Add more complex name comparison algorithms (e.g. arrays, tweaks based on results from equity checks); Add geodata as blocking and more complex comparison variables (pending ch_address_id unduplication)
Update - functional/structural | Designed and implemented postprocessing algorithm that creates match crosswalk | Streamlined and modularized pipeline to reduce dependencies and remove obsolete code; Created configuration module and central control script to allow for better documentation and fast rerun; Generates and logs key match metrics (e.g. # IDs matched) automatically; Created script to join crosswalk to original data; | Created option to use user-defined acceptance criteria instead of default for each pass for project-specific matches (define in config.py) | Added preprocessing template - created middle name aliases when people have multiple middle names Cleaned up various modules and standardized output names | Fixed performance issue with large datasets: matching no longer holds all data in memory; drops blocking tables once used Move sorting from postprocessing to matching; Functions for printing out record pairs for easy clerical review; | Streamlined dedup blocking code Fixed bugs from upgrade to pandas 2 Fixed bugs in 1:M match rate calculation | Update workflow to have a csv path and a postgres path Clean up pipeline to have better integration with the preprocessing component More user-friendly config (yaml files, split preprocessing, etc.) Handle matches with multiple IDs, potentially with different strengths Draft and pilot match analysis to include in linkage memo; | Pilot sampling and reviewing functions to test what is desirable and how it could fit into the workflow; Pilot intersectional equity checks, the results of which informs directions to expand on name matching; | Integrate automated intersectional equity check into post-match reporting; Integrate automated full match analysis in linkage memo; Find sustainable ways to block on large data (DCFS) - maybe breaking blocking passes;
Update - documentation/other | N/A | Created full README | N/A |  |  |  | Draft user manual; Planning for case studies of sensitivity testing |  | Create working version of user manual
Official links produced | N/A | SY21-22 YDC except for CHA undup (CPS undup, YG-CPS, ASM-CPS, CHA-CPS, DFSS-CPS, BUILD-CPS) | SY22-23 Oak Park (preprocessing was separate) Family Networks first-round dedup (subset of DCFS data) | SY22-23 CPS undup SY22-23 YDC except for CHA undup match portion (CPS undup, ASM-CPS, preproc and postproc of CHA undup, CHA-CPS, [Tentative] DFSS-CPS, [Tentative] YG-CPS, [Tentative] BUILD-CPS) Family Networks second-round dedup within household | [Tentative] DCFS undup 2021 DCFS undup 2023?
Tests run | SY20-21 YG-CPS, DCFS undup 2019 (Cook county only) | SY20-21 YDC except for CHA undup, DCFS undup 2019 (Cook county only) | DCFS undup 2019 | SY21-22 CPS, YG, ASM, CHA, BUILD | DCFS undup 2021 |  | Test match results between other admin datasets (e.g. CHILD-CCALD, other active links) and compare with BigMatch results
Link to logic | n/a |  |  | Same as v1.1 | Same as v1.1 | Same as v1.1
Link to commit |  |  | tbd | tbd | tbd
Key constraints | Logic not ready to use for production | Only applies to matches in the same county; Imports legacy preprocessed files in fwf format, and the tool begins applicable there; | Imports legacy preprocessed files in fwf format, and the tool begins applicable there; Can't compare multiple common IDs; Can't add additional blocking passes, because relationship between pass number and acceptance criteria is hard coded; | Can't compare multiple common IDs; Can't add additional blocking passes, because relationship between pass number and acceptance criteria is hard coded;
Note on D11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I need to think on this and double-check some things, but I think with the new way I set up the acceptance criteria we might be able to add multiple common ids or additional blocks, since the pass number and acceptance criteria are no longer hard coded.